Ordered, not received
Validate servo performance in simulation
Order Dongbu servo brackets
Procure stock AEG parts
Not started
Test fire AEG w/ lab supply
Order AEG 3D parts
Complete
Verify servo
current draw
under load.
What torque can be used continuously w/o overheating.
Order test battery
Select computer and camera
Select/order motor driver for AEG
Assemble 3D printed AEG
Proof of concept gait generation
Full BOM, block diagram, and mounting concept
Order full complement of servos
Design chassis plates
Design turret
Design/build power distribution and comms board
Software :)
Construct chassis plates
Construct turret
Assemble
Demo Video
Order spares for all subsystems
Build tool kit
"MJ mech" (provisional name)
Work Plan, 2014-02-15
Josh Pieper, jjp@pobox.com
Test